## Home
MG UNIVERSITY
Version of application : |  | Module name : Home |  |  | Tested by : Sadhika S
Verified by : Pradeep K C |  | Environment Details : Windows 11 |  |  | Date : 15-10-2023
Test id | Test Description | Test Procedure | Test Data | Exp Result | Actual Result | Status
MG_HM_01 | Check whether the website opens when a user enters a valid URL. | Open website www.mgu.ac.in | www.mgu.ac.in | The website should open when the user enters the URL. | The website opens when the user enters the URL. | Pass
MG_HM_02 | Check whether the website is secured with a URL. | Open website www.mgu.ac.in | www.mgu.ac.in | The website should be secured and should have the HTTPS protocol. | The website is secured and has the HTTPS protocol. | Pass
MG_HM_03 | Ensure that the website has a valid certificate. | Open website www.mgu.ac.in | www.mgu.ac.in | The website should have a valid certificate. | The website should has a valid certificate. | Pass
MG_HM_04 | Ensure that the website name is displayed at the top of the page when the user opens www.mgu.ac.in | 1.Open website www.mgu.ac.in 2.Locate the name "Mahatma Gandhi University,Kerala" at the top of the webpage. | www.mgu.ac.in | The website name should be displayed at the top of the page. | The website name is displayed at the top of the page. | Pass
MG_HM_05 | Verify if the website logo is located at the top of the webpage. | 1.Open website www.mgu.ac.in 2.Locate the logo at the top of the webpage. | www.mgu.ac.in | The website logo should be positioned at the top of the page. | The website logo is positioned at the top of the page. | Pass
MG_HM_06 | Verify if the website scroll bar functions correctly. | Open website www.mgu.ac.in | www.mgu.ac.in | The website scroll bar should function correctly. | The website scroll bar functions correctly. | Pass
MG_HM_07 | Ensure that when the user clicks the 'Home' section again, the homepage reloads | 1.Open website www.mgu.ac.in 2.Locate the 'Home' section. | www.mgu.ac.in | When the user clicks the 'Home' section again, it should reload the homepage. | When the user clicks the 'Home' section again, it reloads the homepage. | Pass
MG_HM_08 | Check whether the main image in the 'Home' tab changes randomly in a slideshow manner. | Open website www.mgu.ac.in | www.mgu.ac.in | The main image in the 'Home' tab should change randomly in a slideshow manner. | The main image in the 'Home' tab changes randomly in a slideshow manner. | Pass
MG_HM_09 | Check whether the next button works properly in the main image displayed in slideshow. | Open website www.mgu.ac.in | www.mgu.ac.in | The next button should display next image. | The next button displays next image. | Pass
MG_HM_10 | Check whether the previous button works properly in the main image displayed in slideshow. | Open website www.mgu.ac.in | www.mgu.ac.in | The previous button should display previous image in the slideshow. | The previous button does not display previous image in the slideshow. | Fail
MG_HM_11 | Check whether the 'Search' section on the top right corner enables the user to type. | 1.Open website www.mgu.ac.in 2.Locate the Search bar at the top of the webpage. | www.mgu.ac.in | The 'Search' bar must enable the user to type the input. | The 'Search' bar enables the user to type the input. | Pass
MG_HM_12 | Ensure that the 'Search' bar shows the saved data when a new data is entered. | 1.Open website www.mgu.ac.in 2.Locate the Search bar at the top of the webpage. 3.Click on the Search bar. | www.mgu.ac.in | The 'Search' bar must show the saved data when a new data is entered. | The 'Search' bar shows the saved data when a new data is entered. | Pass
MG_HM_13 | Check whether the language bar below the Search field on top right corner allows the user to switch the language to Malayalam/English (ML/EN). | 1.Open website www.mgu.ac.in 2.Locate the Language(ML/EN) bar at the top of the webpage. 3.Click on ML to view the webpage in Malayalam 4.Click on EN to view the webpage in English. | www.mgu.ac.in | The language of the webpage must change according to the selection of ML/EN. | The language of the webpage changes according to the selection of ML/EN. | Pass
MG_HM_14 | Verify that when the user clicks on the 'Flash News' section, each news redirects to a new page depending on the news. | 1.Open website www.mgu.ac.in 2.Locate Flash News section. 3.Click on Flash News. | www.mgu.ac.in | When the user clicks 'Flash News',each 'Flash News' must redirect to a new page. | When the user clicks 'Flash News',each 'Flash News' redirects to a new page. | Pass
MG_HM_15 | Check whether the user can view the YouTube video,pause and view in full screen mode. | 1.Open website www.mgu.ac.in 2.Locate MGU-Faculty Recruitment 2023. 3.Click Read more. 4.Pause and play again the video. | www.mgu.ac.in | The YouTube video should be paused and then again played in full-screen mode. | The YouTube video can be paused and then again played in full-screen mode. | Pass
MG_HM_16 | Ensure that the user can share the YouTube video on social media. | 1.Open website www.mgu.ac.in 2.Locate MGU-Faculty Recruitment 2023. 3.Click Read more. 4.Click the Share button. | www.mgu.ac.in | The user must be able to share the YouTube video. | The user is able to share the YouTube video. | Pass
MG_HM_17 | Check whether the 'Announcements' displayed below the Flash news is clickable. | 1.Open website www.mgu.ac.in 2.Locate Announcements. 3. Click on Announcements. | www.mgu.ac.in | The Announcements in the webpage must be clickable. | The Announcements in the webpage is clickable. | Pass
MG_HM_18 | Verify that the 'View All' bar of Announcements section displays all the recent announcements. | 1.Open website www.mgu.ac.in 2.Locate View All in the Announcements section. 3.Click on View All. | www.mgu.ac.in | The View All must load a new page of past announcements. | The View All loads a new page of past announcements. | Pass
MG_HM_19 | Ensure that when a user clicks the 'Admission 2023' , it loads the Admissions Portal page. | 1.Open website www.mgu.ac.in 2.Locate Admission 2023. 3.Click on Admission 2023. | www.mgu.ac.in | When the user clicks Read more, the webpage must load Admissions Portal page. | When the user clicks Read more, the webpage loads Admissions Portal page. | Pass
MG_HM_20 | Ensure that when a user clicks the 'Online Application' , it loads the Online Application Portal page. | 1.Open website www.mgu.ac.in 2.Locate Online Application. 3.Click on Online Application. | www.mgu.ac.in | When the user clicks, the webpage must load Online Applications page. | When the user clicks, the webpage loads Online Applications page. | Pass
MG_HM_21 | Ensure that when a user clicks the 'Online Payment' , it loads the MGU e-Pay electronic payment page. | 1.Open website www.mgu.ac.in 2.Locate Online Payment. 3.Click on Online Payment. | www.mgu.ac.in | The webpage must load MGU e-Pay electronic payment page. | The webpage loads MGU e-Pay electronic payment page. | Pass
MG_HM_22 | Ensure that when a user clicks the 'Exam Registration' , it loads the Supplementary Exam Registration page. | 1.Open website www.mgu.ac.in 2.Locate Exam Registration. 3.Click on Exam Registration. | www.mgu.ac.in | The webpage must load Supplementary exam registration page. | The webpage loads Supplementary exam registration page. | Pass
MG_HM_23 | Ensure that when a user clicks the 'Results' , it loads the exam results page. | 1.Open website www.mgu.ac.in 2.Locate Results 3.Click on Results. | www.mgu.ac.in | The webpage must load exam results page. | The webpage loads exam results page. | Pass
MG_HM_24 | Ensure that when a user clicks the 'Student's Grievances' , it loads the MGU Grievance page. | 1.Open website www.mgu.ac.in 2.Locate Student's Grievances. 3.Click on Student's Grievances. | www.mgu.ac.in | The webpage must load MGU Grievance page. | The webpage loads MGU Grievance page. | Pass
MG_HM_25 | Ensure that when a user clicks the 'Online Certificate Portal' , it loads the Online Application for certificates page. | 1.Open website www.mgu.ac.in 2.Locate Online Certificate Portal. 3.Click on Online Certificate Portal. | www.mgu.ac.in | The webpage must load Online application for certificates page. | The webpage must load Online application for certificates page. | Pass
MG_HM_26 | Ensure that when a user clicks the 'Revaluation Portal' , it loads the Revaluation Portal page. | 1.Open website www.mgu.ac.in 2.Locate Revaluation Portal. 3.Click on Revaluation Portal. | www.mgu.ac.in | The webpage must load Revaluation portal page. | The webpage loads Revaluation portal page. | Pass
MG_HM_27 | Ensure that when a user clicks the 'Research Highlights' , it loads the Research page. | 1.Open website www.mgu.ac.in 2.Locate Research Highlights. 3.Click on Research Highlights. | www.mgu.ac.in | The webpage must load Research page. | The webpage loads Research page. | Pass
MG_HM_28 | Ensure that when a user clicks the 'International Students Admission Portal' , it loads the MG Foreign Admission page. | 1.Open website www.mgu.ac.in 2.Locate International Students Admission Portal. Cllick on International Students Admission Portal. | www.mgu.ac.in | The webpage must load MG Foreign Admission page. | The webpage loads MG Foreign Admission page. | Pass
MG_HM_29 | Ensure that when a user clicks any of the options in 'Quick Links' it redirects to a new page based on the given matter. | 1.Open website www.mgu.ac.in 2.Locate Quick Links. 3.Click on any given option. | www.mgu.ac.in | The webpage should load a new page based on the given matter. | The webpage loads a new page based on the given matter. | Pass
MG_HM_30 | Verify that when a user clicks 'IQAC' logo,it loads the Internal Quality Assurance Cell page. | 1.Open website www.mgu.ac.in 2.Locate IQAC. 3.Click on IQAC. | www.mgu.ac.in | The webpage should load a new page of IQAC. | The webpage loads a new page of IQAC. | Pass
MG_HM_31 | Verify that when a user clicks 'Swayam' logo,it loads a new page of Swayam MOOC course. | 1.Open website www.mgu.ac.in 2.Locate Swayam. 3.Click on Swayam. | www.mgu.ac.in | The webpage should load a new page of Swayam MOOC course. | The webpage loads a new page of Swayam MOOC course. | Pass
MG_HM_32 | Verify that when a user clicks 'STRIDE' logo,it loads a new page of e-learning resources. | 1.Open website www.mgu.ac.in 2.Locate STRIDE. 3.Click on STRIDE. | www.mgu.ac.in | The webpage should load a new page of e-learning resources. | The webpage loads a new page of e-learning resources. | Pass
MG_HM_33 | Verify that when a user clicks 'Civil Service Institute' logo, it loads the detail of Civil Service Institute. | 1.Open website www.mgu.ac.in 2.Locate Civil Service Institute. 3.Click on Civil Service Institute. | www.mgu.ac.in | The webpage should load a new page of details of Civil Service Institute. | The webpage loads a new page of details of Civil Service Institute. | Pass
MG_HM_34 | Verify that when a user clicks 'Nirmmalam-MGU' logo, it loads a new page in detail about the green protocol. | 1.Open website www.mgu.ac.in 2.Locate Nirmmalam-MGU. 3.Click on Nirmmalam-MGU. | www.mgu.ac.in | The webpage should load a new page of green protocol. | The webpage loads a new page of green protocol. | Pass
MG_HM_35 | Verify that when a user clicks on the bottom left corner of the Facebook icon, it loads the Facebook login page. | 1.Open website www.mgu.ac.in 2.Locate the Facebook icon. 3.Click on Facebook icon. | www.mgu.ac.in | The webpage should load the facebook login page. | The webpage loads the facebook login page. | Pass
MG_HM_36 | Verify that when a user clicks on the bottom left corner of the Twitter icon, it loads the Twitter login page. | 1.Open website www.mgu.ac.in 2.Locate the Twitter icon. 3.Click on Twitter icon. | www.mgu.ac.in | The webpage should load the twitter login page at the bottom left corner. | The webpage does not load the twitter login page at the bottom left corner. | Fail
MG_HM_37 | Verify that when a user clicks on the bottom left corner of the YouTube icon, it loads the YouTube link in a new page. | 1.Open website www.mgu.ac.in 2.Locate the YouTube icon. 3.Click on YouTube icon. | www.mgu.ac.in | The webpage should load the YouTube link of MG University,Kerala. | The webpage loads the YouTube link of MG University,Kerala. | Pass
MG_HM_38 | Check whether the 'Careers' option loads the Vacancies page. | 1.Open website www.mgu.ac.in 2.Locate Careers. 3.Click on Careers. | www.mgu.ac.in | The webpage should load the Vacancies Archives page. | The webpage loads the Vacancies Archives page. | Pass
MG_HM_39 | Check whether the 'Terms of Use' option is clickable and loads a new page. | 1.Open website www.mgu.ac.in 2.Locate Terms of Use. 3.Click on Terms of Use. | www.mgu.ac.in | The webpage should load the Terms of Use page. | The webpage loads the Terms of Use page. | Pass
MG_HM_40 | Check whether the 'RTI' option loads the Right to Information page. | 1.Open website www.mgu.ac.in 2.Locate RTI. 3.Click on RTI. | www.mgu.ac.in | The webpage should load the Right to Information page. | The webpage loads the Right to Information page. | Pass
MG_HM_41 | Check whether the 'Sitemap' option is clickable and loads a new page. | 1.Open website www.mgu.ac.in 2.Locate Sitemap. 3.Click on Sitemap. | www.mgu.ac.in | The webpage should load a new page of sitemap. | The webpage loads a new page of sitemap. | Pass
MG_HM_42 | Check whether the 'Reports' option loads reports page. | 1.Open website www.mgu.ac.in 2.Locate Reports. 3.Click on Reports. | www.mgu.ac.in | The webpage should load Reports page. | The webpage loads the Reports page. | Pass
MG_HM_43 | Check whether the 'Minutes' option loads minutes page. | 1.Open website www.mgu.ac.in 2.Locate Minutes. 3.Click on Minutes. | www.mgu.ac.in | The webpage should load the minutes page. | The webpage loads the minutes page. | Pass
MG_HM_44 | Check whether the 'Quotations & Tenders' option loads Tenders page. | 1.Open website www.mgu.ac.in 2.Locate Quotations & Tenders. 3.Click on Quotations & Tenders. | www.mgu.ac.in | The webpage should load the Quotations & Tenders page. | The webpage loads the Quotations & Tenders page. | Pass
MG_HM_45 | Check whether the 'Old Question Papers' option loads Model Question Papers page. | 1.Open website www.mgu.ac.in 2.Locate Old Question Papers. 3.Click on Old Question Papers. | www.mgu.ac.in | The webpage should load Old question papers page. | The webpage loads Old question papers page. | Pass
MG_HM_46 | Check whether the 'FAQ' option is clickable and loads FAQ Archive page. | 1.Open website www.mgu.ac.in 2.Locate FAQ. 3.Click on FAQ. | www.mgu.ac.in | The webpage should load the FAQ Archive page. | The webpage loads the FAQ Archive page. | Pass
MG_HM_47 | Check whether the 'Higher Education Department' option loads the Higher Education Department page. | 1.Open website www.mgu.ac.in 2.Locate Higher Education Department. 3.Click on Higher Education Department. | www.mgu.ac.in | The webpage should load the Higher Education Department page. | The webpage loads the Higher Education Department page. | Pass
MG_HM_48 | Check whether the 'SOAFT' option loads the online application for foreign travel page. | 1.Open website www.mgu.ac.in 2.Locate SOAFT. 3.Click on SOAFT. | www.mgu.ac.in | The webpage should load the online application for foreign travel page. | The webpage loads the online application for foreign travel page. | Pass
MG_HM_49 | Check whether the 'Kerala Job Portal' option loads the job portal page. | 1.Open website www.mgu.ac.in 2.Locate Kerala Job Portal. 3.Click on Kerala Job Portal. | www.mgu.ac.in | The webpage should load the job portal page. | The webpage should loads the job portal page. | Pass
MG_HM_50 | Check whether the 'Kerala Battles Covid' option loads the covid details page. | 1.Open website www.mgu.ac.in 2.Locate Kerala Battles Covid. 3.Click on Kerala Battles Covid. | www.mgu.ac.in | The webpage should load the covid details page. | The webpage loads the covid details page. | Pass
MG_HM_51 | Check whether the 'National Academic Depository' option loads government's DigiLocker page. | 1.Open website www.mgu.ac.in 2.Locate National Academic Depository. 3.Click on National Academic Repository. | www.mgu.ac.in | The webpage should load the DigiLocker page. | The webpage loads the DigiLocker page. | Pass
MG_HM_52 | Check whether the 'Contact Us' option is available on the webpage. | 1.Open website www.mgu.ac.in 2.Locate Contact Us. 3.Click on Contact Us. | www.mgu.ac.in | The webpage should load the contact details of the university. | The webpage loads the contact details of the university. | Pass
MG_HM_53 | Verify that the copyright section is added on the webpage. | Open website www.mgu.ac.in | www.mgu.ac.in | The copyright section should be present in the webpage. | The copyright section is present in the webpage. | Pass
MG_HM_54 | Check whether the 'Read more' option given below each article is clickable and redirects to a detailed new article respectively. | 1.Open website www.mgu.ac.in 2.Locate Read more. | www.mgu.ac.in | The 'Read more' option must be clickable and should load a new article page. | The 'Read more' option is clickable and loads a new article page. | Pass

## About
MG UNIVERSITY
Version of application : |  | Module name : About |  |  | Tested by : Sadhika S
Verified by : Pradeep K C |  | Environment Details : Windows 11 |  |  | Date : 19-10-2023
Test id | Test Description | Test Procedure | Test Data | Exp Result | Actual Result | Status
MG_AB_01 | Verify that when a user clicks 'About' option, a new page is loaded. | 1.Open website www.mgu.ac.in 2.Locate the 'About' section. |  | When the user clicks the 'About' section, it should load a new page. | When the user clicks the 'About' section, it loads a new page. | Pass
MG_AB_02 | Verify that when a user clicks 'About' tab, the field gets highlighted. | 1.Open website www.mgu.ac.in 2.Locate the 'About' section. |  | When the user clicks the 'About' tab, it should get highlighted. | When the user clicks the 'About' tab, it does not gets highlighted. | Fail
MG_AB_03 | Ensure that university details are displayed under the 'About' heading. | 1.Open website www.mgu.ac.in 2.Locate the 'About' section. |  | University details must be displayed under 'About' heading. | University details is displayed under 'About' heading. | Pass
MG_AB_04 | Verify that 'About' section's font style and font size makes the text easily readable and visible to the user. | 1.Open website www.mgu.ac.in 2.Locate the 'About' section. |  | About' section's font style and font size should make the text easily readable and visible to the user. | About' section's font style and font size makes the text easily readable and visible to the user. | Pass
MG_AB_05 | Verify if the website scroll bar functions correctly. | 1.Open website www.mgu.ac.in 2.Locate the 'About' section. |  | The website scroll bar should function correctly. | The website scroll bar functions correctly. | Pass
MG_AB_06 | Check whether the dropdown under 'About' functions correctly. | 1.Open website www.mgu.ac.in 2.Locate the 'About' section. |  | The dropdown under 'About' must function correctly. | The dropdown under 'About' functions correctly. | Pass
MG_AB_07 | Check whether the 'Overview' under About displays detail of the university. | 1.Open website www.mgu.ac.in 2.Locate 'Overview' from the About section. |  | The Overview must display an explanation of the university. | The Overview displays an explanation of the university. | Pass
MG_AB_08 | Check whether the 'IQAC' under About loads a new page. | 1.Open website www.mgu.ac.in 2.Locate 'IQAC' from the About section. |  | The IQAC must load a new page of the same. | The IQAC loads a new page of the same. | Pass
MG_AB_09 | Check whether the 'Ranking & Accreditation' under About loads a new page. | 1.Open website www.mgu.ac.in 2.Locate 'Ranking & Accreditation' from the About section. |  | The Ranking & Accreditation must load a new page. | The Ranking & Accreditation loads a new page. | Pass
MG_AB_10 | Check whether the 'Achievements' under About loads the achievements of MG university page. | 1.Open website www.mgu.ac.in 2.Locate 'Achievements' from the About section. |  | The Achievements must load a new page of achievements of MG university. | The Achievements loads a new page of achievements of MG university. | Pass
MG_AB_11 | Check whether the 'Disclosure' under About loads a new page. | 1.Open website www.mgu.ac.in 2.Locate 'Disclosure' from the About section. |  | The Disclosure must load a new page. | The Disclosure loads a new page. | Pass
MG_AB_12 | Check whether the 'RTI' under About loads a new page. | 1.Open website www.mgu.ac.in 2.Locate 'RTI' from the About section. |  | The RTI must load a page of Right to Information. | The RTI loads a page of Right to Information. | Pass
MG_AB_13 | Check whether the 'Organisational chart' under About loads a new page. | 1.Open website www.mgu.ac.in 2.Locate 'Organisational Chart' from the About section. |  | The Organisational Chart must load a new page. | The Organisational Chart loads a new page. | Pass
MG_AB_14 | Check whether the 'Work Distribution' under About loads a new page. | 1.Open website www.mgu.ac.in 2.Locate 'Work Distribution' from the About section. |  | The Work Distribution must load a new page. | The Work Distribution loads a new page. | Pass

## Administration
MG UNIVERSITY
Version of application : |  | Module name : Administration |  |  | Tested by : Sadhika S
Verified by : Pradeep K C |  | Environment Details : Windows 11 |  |  | Date : 25-10-2023
Test id | Test Description | Test Procedure | Test Data | Exp Result | Actual Result | Status
MG_AD_01 | Verify that when a user clicks 'Administration' option, a new page is loaded. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section. |  | When the user clicks the 'Administration' section, it should load a new page. | When the user clicks the 'Administration' section, it loads a new page. | Pass
MG_AD_02 | Verify that the section 'Administration' contains a dropdown menu list. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section. |  | The section 'Administration' should have a dropdown menu list. | The section 'Administration' has a dropdown menu list. | Pass
MG_AD_03 | Verify that when a user clicks 'Administration' tab, the field gets highlighted. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section. |  | When the user clicks the 'Administration' tab, it should get highlighted. | When the user clicks the 'Administration' tab, it does not gets highlighted. | Fail
MG_AD_04 | Check whether clicking on the 'Administration' submenu 'The Chancellor' loads the chancellor's detail on a new page. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section. 3.Click on 'The Chancellor' submenu. |  | When the user clicks on the 'Administration' submenu 'The Chancellor', it should load the details of the Chancellor. | When the user clicks on the 'Administration' submenu 'The Chancellor', it loads the details of the Chancellor. | Pass
MG_AD_05 | Check whether clicking on the 'Administration' submenu 'The Pro Chancellor' loads the chancellor's detail on a new page. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'The Pro Chancellor' submenu. |  | When the user clicks on the 'Administration' submenu 'The Pro Chancellor', it should load the details of the Pro Chancellor. | When the user clicks on the 'Administration' submenu 'The Pro Chancellor', it loads the details of the Pro Chancellor. | Pass
MG_AD_06 | Check whether clicking on the 'Administration' submenu 'Vice Chancellor' loads the chancellor's detail on a new page. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Vice Chancellor' submenu. |  | When the user clicks on the 'Administration' submenu 'Vice Chancellor', it should load the details of the Vice Chancellor. | When the user clicks on the 'Administration' submenu 'Vice Chancellor', it loads the details of the Vice Chancellor. | Pass
MG_AD_07 | Check whether clicking on the 'Administration' submenu 'Pro-Vice Chancellor' loads the chancellor's detail on a new page. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Pro-Vice Chancellor' submenu. |  | When the user clicks on the 'Administration' submenu 'Pro-Vice Chancellor', it should load the details of the Pro-Vice Chancellor. | When the user clicks on the 'Administration' submenu 'Pro-Vice Chancellor', it does not load the details of the Pro-Vice Chancellor and 'page not found' meassage comes. | Fail
MG_AD_08 | Check whether clicking on the 'Administration' submenu 'Statutory Bodies' loads a new page of a list of statutory bodies. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Statutory Bodies' submenu. |  | When the user clicks on the 'Administration' submenu 'Statutory Bodies', it should load a new page of a list of statutory bodies. | When the user clicks on the 'Administration' submenu 'Statutory Bodies', it loads a new page of a list of statutory bodies. | Pass
MG_AD_09 | Check whether clicking the 'Syndicate' submenu of Statutory Bodies loads the contact details of the members of the Syndicate. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Statutory Bodies' submenu. 3.Click on 'Syndicate'. |  | When the user clicks on 'Syndicate' under the submenu 'Statutory Bodies', it should load the contact details of the members of the syndicate. | When the user clicks on 'Syndicate' under the submenu 'Statutory Bodies', it loads the contact details of the members of the syndicate. | Pass
MG_AD_10 | Verify that clicking on the 'Syndicate Standing Committee' present at the end of the Members of Syndicate page loads a pdf of committee members. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Statutory Bodies' submenu. 3.Click on the 'Syndicate Standing Committee' under 'Syndicate'. |  | When the user clicks on 'Syndicate Standing Committee' under the submenu 'Syndicate', it should load a pdf of committee members. | When the user clicks on 'Syndicate Standing Committee' under the submenu 'Syndicate', it loads a pdf of committee members. | Pass
MG_AD_11 | Check whether clicking the 'Senate' submenu of Statutory Bodies loads the latest list of senate members pdf. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Senate' submenu of Statutory Bodies. |  | When the user clicks 'Senate' under the submenu 'Statutory Bodies', it should load a pdf of the latest list of senate members. | When the user clicks 'Senate' under the submenu 'Statutory Bodies', it loads a pdf of the latest list of senate members. | Pass
MG_AD_12 | Check whether clicking the 'Academic Council' submenu of Statutory Bodies loads the list of academic council members. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Academic Council' submenu of Statutory Bodies. |  | When the user clicks 'Academic Council' under the submenu 'Statutory Bodies', it should load a pdf of the list of academic council members. | When the user clicks 'Academic Council' under the submenu 'Statutory Bodies', it loads a pdf of the list of academic council members. | Pass
MG_AD_13 | Check whether clicking the 'Deans of Faculty' submenu of Statutory Bodies loads the latest list of deans of faculties. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Deans of Faculty' submenu of Statutory Bodies. |  | When the user clicks 'Deans of Faculty' under the submenu 'Statutory Bodies', it should load the latest list of deans of faculties. | When the user clicks 'Deans of Faculty' under the submenu 'Statutory Bodies', it loads the latest list of deans of faculties. | Pass
MG_AD_14 | Check whether clicking the 'Statutory Finance Committee' submenu of Statutory Bodies loads the latest list of statutory finance committee. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Statutory Finance Committee' submenu of Statutory Bodies. |  | When the user clicks 'Statutory Finance Committee' under the submenu 'Statutory Bodies', it should load the latest list of Statutory finance committee. | When the user clicks 'Statutory Finance Committee' under the submenu 'Statutory Bodies', it loads the latest list of Statutory finance committee. | Pass
MG_AD_15 | Check whether clicking the 'Board of Studies UG' submenu of Statutory Bodies loads the latest list of UG board of studies members. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Board of Studies UG' submenu of Statutory Bodies. |  | When the user clicks 'Board of Studies UG' under the submenu 'Statutory Bodies', it should load the latest list of UG board of studies members. | When the user clicks 'Board of Studies UG' under the submenu 'Statutory Bodies', it loads the latest list of UG board of studies members. | Pass
MG_AD_16 | Check whether clicking the 'Board of Studies PG' submenu of Statutory Bodies loads the latest list of PG board of studies members. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Board of Studies PG' submenu of Statutory Bodies. |  | When the user clicks 'Board of Studies PG' under the submenu 'Statutory Bodies', it should load the latest list of PG board of studies members. | When the user clicks 'Board of Studies PG' under the submenu 'Statutory Bodies', it loads the latest list of PG board of studies members. | Pass
MG_AD_17 | Check whether clicking the 'Board of Studies UG/PG combined' submenu of Statutory Bodies loads the latest list of PG board of studies members. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Board of Studies UG/PG combined' submenu of Statutory Bodies. |  | When the user clicks 'Board of Studies UG/PG combined' under the submenu 'Statutory Bodies', it should load the latest list of UG/PG combined board of studies members. | When the user clicks 'Board of Studies UG/PG combined' under the submenu 'Statutory Bodies', it loads the latest list of UG/PG combined board of studies members. | Pass
MG_AD_18 | Check whether clicking the 'Board for Adjudication of Students Grievances (BASG)' submenu of Statutory Bodies loads the latest list of BASG. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Board for Adjudication of Students Grievances (BASG)' submenu of Statutory Bodies. |  | When the user clicks 'Board for Adjudication of Students Grievances (BASG)' under the submenu 'Statutory Bodies', it should load the latest list of BASG. | When the clicks 'Board for Adjudication of Students Grievances (BASG)' under the submenu 'Statutory Bodies', it loads the latest list of BASG. | Pass
MG_AD_19 | Ensure that 'Board of Studies in Departments of the University' submenu under Statutory Bodies is clickable. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Board of Studies in Departments of the University' submenu of Statutory Bodies. |  | 'Board of Studies in Departments of the University' submenu under Statutory Bodies must be clickable. | 'Board of Studies in Departments of the University' submenu under Statutory Bodies is not clickable. | Fail
MG_AD_20 | Ensure that 'Students Council' submenu under Statutory Bodies is clickable. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Students Council' submenu of Statutory Bodies. |  | 'Students Council' submenu under Statutory Bodies must be clickable. | 'Students Council' submenu under Statutory Bodies is not clickable. | Fail
MG_AD_21 | Check whether clicking on the 'Administration' submenu 'Registrar' loads the academic profile of the registrar. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Registrar' submenu. |  | When the user clicks on the 'Administration' submenu 'Registrar', it should load the academic details of the registrar. | When the user clicks on the 'Administration' submenu 'Registrar', it loads the academic details of the registrar. | Pass
MG_AD_22 | Check whether clicking on the 'Administration' submenu 'Controller of Examinations' loads the details of the controller. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Controller of Examinations' submenu. |  | When the user clicks on the 'Administration' submenu 'Controller of Examinations', it should load the details of the controller. | When the user clicks on the 'Administration' submenu 'Controller of Examinations', it loads the details of the controller. | Pass
MG_AD_23 | Check whether clicking on the 'Administration' submenu 'Finance Officer' loads the details of the finance officer. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Finance Officer' submenu. |  | When the user clicks on the 'Administration' submenu 'Finance Officer', it should load the details of the finance officer. | When the user clicks on the 'Administration' submenu 'Finance Officer', it loads the details of the finance officer. | Pass
MG_AD_24 | Check whether clicking on the 'Administration' submenu 'Other Statutory Officers' loads the list of the statutory officers. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Other Statutory Officers' submenu. |  | When the user clicks on the 'Administration' submenu 'Other Statutory Officers', it should load the list of the statutory officers. | When the user clicks on the 'Administration' submenu 'Other Statutory Officers', it loads the list of the statutory officers. | Pass
MG_AD_25 | Check whether clicking the 'Joint Registrars' submenu of Other Statutory Officers loads the contact details of the joint registrars. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Joint Registrars' submenu of Other Statutory Officers. |  | When the user clicks on the 'Joint Registrars' submenu 'Other Statutory Officers', it should load the contact details of the joint registrars. | When the user clicks on the 'Joint Registrars' submenu 'Other Statutory Officers', it loads the contact details of the joint registrars. | Pass
MG_AD_26 | Check whether clicking the 'Deputy Registrars' submenu of Other Statutory Officers loads the contact details of the deputy registrars. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Deputy Registrars' submenu of Other Statutory Officers. |  | When the user clicks on the 'Deputy Registrars' submenu 'Other Statutory Officers', it should load the contact details of the deputy registrars. | When the user clicks on the 'Deputy Registrars' submenu 'Other Statutory Officers', it loads the contact details of the deputy registrars. | Pass
MG_AD_27 | Check whether clicking the 'Assistant Registrars' submenu of Other Statutory Officers loads the contact details of the assistant registrars. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Assistant Registrars' submenu of Other Statutory Officers. |  | When the user clicks on the 'Assistant Registrars' submenu 'Other Statutory Officers', it should load the contact details of the assistant registrars. | When the user clicks on the 'Assistant Registrars' submenu 'Other Statutory Officers', it loads the contact details of the assistant registrars. | Pass
MG_AD_28 | Check whether clicking the 'Personal Staff' submenu of Other Statutory Officers loads the contact details of the personal staffs of each office. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Personal Staff' submenu of Other Statutory Officers. |  | When the user clicks on the 'Personal Staff' submenu 'Other Statutory Officers', it should load the contact details of the personal staffs of each office. | When the user clicks on the 'Personal Staff' submenu 'Other Statutory Officers', it loads the contact details of the personal staffs of each office. | Pass
MG_AD_29 | Check whether clicking on the 'Administration' submenu 'Other Offices' loads the list of offices in the MG university. | 1.Open website www.mgu.ac.in 2.Locate the 'Administration' section and click on 'Other Offices' submenu. |  | When the user clicks on the 'Administration' submenu 'Other Offices', it should load the list of offices in the MG university. | When the user clicks on the 'Administration' submenu 'Other Offices', it loads the list of offices in the MG university. | Pass

## Academics
MG UNIVERSITY
Version of application : |  | Module name : Academics |  |  | Tested by : Sadhika S
Verified by : Pradeep K C |  | Environment Details : Windows 11 |  |  | Date : 28-10-2023
Test id | Test Description | Test Procedure | Test Data | Exp Result | Actual Result | Status
MG_AC_01 | Verify that when a user clicks 'Academics' option, a new page is loaded. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. |  | When the user clicks the 'Academics' section, it should load a new page. | When the user clicks the 'Academics' section, it loads a new page. | Pass
MG_AC_02 | Verify that the section 'Academics' contains a dropdown menu list. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. |  | The section 'Academics' should have a dropdown menu list. | The section 'Academics' has a dropdown menu list. | Pass
MG_AC_03 | Verify that when a user clicks 'Academics' tab, the field gets highlighted. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. |  | When the user clicks the 'Academics' tab, it should get highlighted. | When the user clicks the 'Academics' tab, it does not gets highlighted. | Fail
MG_AC_04 | Check whether clicking on the 'Academics' submenu 'Schools' loads the list and details of the respective schools under MG University. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Schools' submenu. |  | When the user clicks the 'Academics' submenu 'Schools', it should list the details of respective schools under MG University. | When the user clicks the 'Academics' submenu 'Schools', it lists the details of respective schools under MG University. | Pass
MG_AC_05 | Check whether clicking on the 'Academics' submenu 'International Centres' loads the list of international centres in MG University. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'International Centres' submenu. |  | When the user clicks the 'Academics' submenu 'International Centres', it should list the international centres in MG University. | When the user clicks the 'Academics' submenu 'International Centres', it lists the international centres in MG University. | Pass
MG_AC_06 | Check whether clicking on the 'Academics' submenu 'International Centres' , the listed two centres are clickable. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'International Centres' submenu. |  | When the user clicks the 'Academics' submenu 'International Centres', the two centres listed should be clickable. | When the user clicks the 'Academics' submenu 'International Centres', the two centres listed are not clickable. | Fail
MG_AC_07 | Check whether clicking on the 'Academics' submenu 'Inter University Centres' loads the list of centres in MG University and are clickable. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Inter University Centres' submenu. |  | When the user clicks the 'Academics' submenu 'Inter University Centres', it should list the centres in MG University and should be clickable. | When the user clicks the 'Academics' submenu 'Inter University Centres', it lists the centres in MG University and are clickable. | Pass
MG_AC_08 | Check whether clicking on the 'Academics' submenu 'Inter School Centres' loads the list of school centres in MG University and are clickable. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Inter School Centres' submenu. |  | When the user clicks the 'Academics' submenu 'Inter School Centres', it should list the school centres in MG University and should be clickable. | When the user clicks the 'Academics' submenu 'Inter School Centres', it lists the school centres in MG University and are clickable. | Pass
MG_AC_09 | Check whether clicking on the 'Academics' submenu 'Other Centres' , the centres mentioned are clickable. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Other Centres' submenu. |  | When the user clicks the 'Academics' submenu 'Other Centres', the listed centres should be clickable. | When the user clicks the 'Academics' submenu 'Other Centres', the listed centres are clickable. | Pass
MG_AC_10 | Check whether clicking on the 'Academics' submenu 'Affiliated Colleges', the colleges affiliated under MG University are listed in alphabetical order. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Affiliated Colleges' submenu. |  | When the user clicks the 'Academics' submenu 'Affiliated Colleges', the colleges affiliated under MG University should be listed in alphabetical order. | When the user clicks the 'Academics' submenu 'Affiliated Colleges', the colleges affiliated under MG University are listed in alphabetical order. | Pass
MG_AC_11 | Ensure that the 'Search' bar in the 'Affiliated College' submenu is clickable and the textbox is editable. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Affiliated Colleges' submenu. 4.Locate the 'Search' bar. |  | When the user clicks on the Search bar of the 'Affiliated Colleges', the textbox must be editable. | When the user clicks on the Search bar of the 'Affiliated Colleges', the textbox is editable. | Pass
MG_AC_12 | Ensure that the 'District' field in the 'Affiliated Colleges' submenu has a dropdown of the list of districts having MGU colleges. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Affiliated Colleges' submenu. 4.Locate the 'District' bar. |  | When the user clicks on the District field of the 'Affiliated Colleges', the dropdown must show the districts having MGU colleges. | When the user clicks on the District field of the 'Affiliated Colleges', the dropdown shows the districts having MGU colleges. | Pass
MG_AC_13 | Ensure that the 'College Type' field in the 'Affiliated College' submenu has a dropdown of the list of types of colleges. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Affiliated Colleges' submenu. 4.Locate the 'College Type' bar. |  | When the user clicks on the College Type field of the 'Affiliated Colleges', the dropdown must show the list of types of colleges. | When the user clicks on the College Type field of the 'Affiliated Colleges', the dropdown shows the list of types of colleges. | Pass
MG_AC_14 | Check whether clicking on the 'Academics' submenu 'Academic Chairs', loads the Chairs list of people and are clickable. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Academic Chairs' submenu. |  | When the user clicks the 'Academics' submenu 'Academic Chairs', the page must load list of people and should be clickable. | When the user clicks the 'Academics' submenu 'Academic Chairs', the page must load list of people and is clickable. | Pass
MG_AC_15 | Check whether clicking on the 'Academics' submenu 'Programmes', loads the list of programmes in alphabetical order. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Programmes' submenu. |  | When the user clicks the 'Academics' submenu 'Programmes', the page must load list of programmes in alphabetical order. | When the user clicks the 'Academics' submenu 'Programmes', the page loads list of programmes in alphabetical order. | Pass
MG_AC_16 | Ensure that the 'Search' bar in the 'Programmes' submenu is clickable and the textbox is editable. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Programmes' submenu. |  | When the user clicks on the Search bar of the 'Programmes', the textbox must be editable. | When the user clicks on the Search bar of the 'Programmes', the textbox is editable. | Pass
MG_AC_17 | Verify that clicking the 'Syllabus for all programmes' under 'Programmes' submenu loads the syllabus page. | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Programmes' submenu. 4.Locate 'Syllabus for all programmes' submenu. |  | When the user clicks 'Syllabus for all programmes' under 'Programmes' submenu, the page should load the syllabus details. | When the user clicks 'Syllabus for all programmes' under 'Programmes' submenu, the page does not load the syllabus details and 'page not found' message comes. | Fail
MG_AC_18 | Check whether clicking on the 'Academics' submenu 'Syllabus', loads the syllabus for different courses | 1.Open website www.mgu.ac.in 2.Locate the 'Academics' section. 3.Click on 'Syllabus' submenu. |  | When the user clicks the 'Academics' submenu 'Syllabus', the page must load syllabus for different courses. | When the user clicks the 'Academics' submenu 'Syllabus', the page loads syllabus for different courses. | Pass

## Admissions
MG UNIVERSITY
Version of application : |  | Module name : Admissions |  |  | Tested by : Sadhika S
Verified by : Pradeep K C |  | Environment Details : Windows 11 |  |  | Date : 30-10-2023
Test id | Test Description | Test Procedure | Test Data | Exp Result | Actual Result | Status
MG_AM_01 | Verify that when a user clicks 'Admissions' option, a new page is loaded. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. |  | When the user clicks the 'Admissions' section, it should load a new page. | When the user clicks the 'Admissions' section, it loads a new page. | Pass
MG_AM_02 | Verify that the section 'Admissions' contains a dropdown menu list. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. |  | The section 'Admissions' should have a dropdown menu list. | The section 'Admissions' has a dropdown menu list. | Pass
MG_AM_03 | Verify that when a user clicks 'Admissions' tab, the field gets highlighted. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. |  | When the user clicks the 'Admissions' tab, it should get highlighted. | When the user clicks the 'Admissions' tab, it does not gets highlighted. | Fail
MG_AM_04 | Check whether clicking on the 'Admissions' submenu 'Study @MGU- Schools/Centres (CAT)' loads a new page of the same. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'Study @MGU- Schools/Centres (CAT)' submenu. |  | When the user clicks the 'Admissions' submenu 'Study @MGU- Schools/Centres (CAT)', it should load a new page of the same. | When the user clicks the 'Admissions' submenu 'Study @MGU- Schools/Centres (CAT)', it shows an error page. | Fail
MG_AM_05 | Check whether clicking on the 'Admissions' submenu 'Affiliated Colleges UG/PG (CAP)', loads a new page of Centralized Allotment Process. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'Affiliated Colleges UG/PG (CAP)' submenu. |  | When the user clicks the 'Admissions' submenu 'Affiliated Colleges UG/PG (CAP)', it should load a new page of Centralized Allotment Process. | When the user clicks the 'Admissions' submenu 'Affiliated Colleges UG/PG (CAP)', it loads a new page of Centralized Allotment Process. | Pass
MG_AM_06 | Check whether clicking on the 'Admissions' submenu 'B.Ed./M.Ed. -CAP', loads admissions to B.Ed./M.Ed. page. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'B.Ed./M.Ed. -CAP' submenu. |  | When the user clicks the 'Admissions' submenu 'B.Ed./M.Ed. -CAP', it should load admissions to B.Ed./M.Ed. Page. | When the user clicks the 'Admissions' submenu 'B.Ed./M.Ed. -CAP', it loads admissions to B.Ed./M.Ed. Page. | Pass
MG_AM_07 | Check whether clicking on the 'Admissions' submenu 'Non CAP Programmes', loads Others page. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'Non CAP Programmes' submenu. |  | When the user clicks the 'Admissions' submenu 'Non CAP Programmes', it should load Others page. | When the user clicks the 'Admissions' submenu 'Non CAP Programmes', it loads Others page. | Pass
MG_AM_08 | Check whether clicking on the 'Admissions' submenu 'Integrated Programmes', loads a new page of the same. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'Integrated Programmes' submenu. |  | When the user clicks the 'Admissions' submenu 'Integrated Programmes', it should load a new page of the same. | When the user clicks the 'Admissions' submenu 'Integrated Programmes', it does not load a new page and shows an error message. | Fail
MG_AM_09 | Check whether clicking on the 'Admissions' submenu 'M Phil', loads a new page of M Phil in detail. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'M Phil' submenu. |  | When the user clicks the 'Admissions' submenu 'M Phil', it should load a new page of M Phil in detail. | When the user clicks the 'Admissions' submenu 'M Phil', it shows a 'page not found' error message. | Fail
MG_AM_10 | Check whether clicking on the 'Admissions' submenu 'MBA (SMBS)', loads a new page of MBA details. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'MBA (SMBS)' submenu. |  | When the user clicks the 'Admissions' submenu 'MBA (SMBS)', it should load a new page of MBA. | When the user clicks the 'Admissions' submenu 'MBA (SMBS)', it shows an error message. | Fail
MG_AM_11 | Check whether clicking on the 'Admissions' submenu 'Ph.D', loads the Research Portal. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'Ph.D' submenu. |  | When the user clicks the 'Admissions' submenu 'Ph.D', it should load Research Portal. | When the user clicks the 'Admissions' submenu 'Ph.D', it loads the Research Portal. | Pass
MG_AM_12 | Check whether clicking on the 'Admissions' submenu 'International Students Admission', loads MGU Foreign Admission page. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'International Students Admission' submenu. |  | When the user clicks the 'Admissions' submenu 'International Students Admission', it should load MGU Foreign Admission page. | When the user clicks the 'Admissions' submenu 'International Students Admission', it loads MGU Foreign Admission page. | Pass
MG_AM_13 | Check whether clicking on the 'Admissions' submenu 'Private Registration', loads the UG/PG private registration details. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'Private Registration' submenu. |  | When the user clicks the 'Admissions' submenu 'Private Registration', it should load the UG/PG private registration details. | When the user clicks the 'Admissions' submenu 'Private Registration', it loads the UG/PG private registration details. | Pass
MG_AM_14 | Check whether clicking on the 'Admissions' submenu 'Distance Education', loads the School of Distance Education page. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'Distance Education' submenu. |  | When the user clicks the 'Admissions' submenu 'Distance Education', it should load School of Distance Education page. | When the user clicks the 'Admissions' submenu 'Distance Education', it loads School of Distance Education page. | Pass
MG_AM_15 | Check whether clicking on the 'Admissions' submenu 'Online Programmes', loads MGUOnline page. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'Online Programmes' submenu. |  | When the user clicks the 'Admissions' submenu 'Online Programmes', it should load MGUOnline page. | When the user clicks the 'Admissions' submenu 'Online Programmes', it loads MGUOnline page. | Pass
MG_AM_16 | Check whether clicking on the 'Admissions' submenu 'Short-term Programmes (DASP)', loads short-term courses page. | 1.Open website www.mgu.ac.in 2.Locate the 'Admissions' section. 3.Click on 'Short-term Programmes (DASP)' submenu. |  | When the user clicks the 'Admissions' submenu 'Short-term Programmes (DASP)', it should load short-term courses page. | When the user clicks the 'Admissions' submenu 'Short-term Programmes (DASP)', it loads short-term courses page. | Pass

## Examinations
MG UNIVERSITY
Version of application : |  | Module name : Examinations |  |  | Tested by : Sadhika S
Verified by : Pradeep K C |  | Environment Details : Windows 11 |  |  | Date : 31-10-2023
Test id | Test Description | Test Procedure | Test Data | Exp Result | Actual Result | Status
MG_EX_01 | Verify that when a user clicks 'Examinations' option, a new page is loaded. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. |  | When the user clicks the 'Examinations' section, it should load a new page. | When the user clicks the 'Examinations' section, it loads a new page. | Pass
MG_EX_02 | Verify that the section 'Examinations' contains a dropdown menu list. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. |  | The section 'Examinations' should have a dropdown menu list. | The section 'Examinations' has a dropdown menu list. | Pass
MG_EX_03 | Verify that when a user clicks 'Examinations' tab, the field gets highlighted. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. |  | When the user clicks the 'Examinations' tab, it should get highlighted. | When the user clicks the 'Examinations' tab, it does not gets highlighted. | Fail
MG_EX_04 | Check whether clicking on the 'Examinations' submenu 'Examination Notifications' loads a new page of the notification of the upcoming examinations. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Examination Notification' submenu. |  | When the user clicks the 'Examinations' submenu 'Examination Notification', it should load a new page of the notification of the upcoming examinations. | When the user clicks the 'Examinations' submenu 'Examination Notification', it loads a new page of the notification of the upcoming examinations. | Pass
MG_EX_05 | Verify that the previous and next bottons at the bottom of the 'Examination Notification' submenu page is working correctly. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Examination Notification' submenu. 4.Locate the previous and next buttons at the bottom of the page. |  | When the user clicks the 'Examinations' submenu 'Examination Notification', it should load a new page and the previous and next buttons at the bottom of the page must work correctly | When the user clicks the 'Examinations' submenu 'Examination Notification', it loads a new page and the previous and next buttons at the bottom of the page works correctly | Pass
MG_EX_06 | Check whether clicking on the 'Examinations' submenu 'Examination Orders' loads a new page of the orders of examinations conducted. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Examination Orders' submenu. |  | When the user clicks the 'Examinations' submenu 'Examination Orders', it should load a new page of the orders of examinations conducted. | When the user clicks the 'Examinations' submenu 'Examination Orders', it loads a new page of the orders of examinations conducted. | Pass
MG_EX_07 | Verify that the previous and next buttons at the bottom of the 'Examination Orders' submenu page is working correctly. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Examination Orders' submenu. 4.Locate the previous and next buttons at the bottom of the page. |  | When the user clicks the 'Examinations' submenu 'Examination Orders', it should load a new page and the previous and next buttons at the bottom of the page must work correctly. | When the user clicks the 'Examinations' submenu 'Examination Orders', it loads a new page and the previous and next buttons at the bottom of the page works correctly. | Pass
MG_EX_08 | Check whether clicking on the 'Examinations' submenu 'Exam Results' loads a new page of the orders of examinations conducted. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Exam Results' submenu. |  | When the user clicks the 'Examinations' submenu 'Exam Results', it should load Results page. | When the user clicks the 'Examinations' submenu 'Exam Results', it loads Results page. | Pass
MG_EX_09 | Check whether clicking on the 'Examinations' submenu 'Exam Time Tables' loads a new page of the time tables of examinations. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Exam Time Tables' submenu. |  | When the user clicks the 'Examinations' submenu 'Exam Time Tables', it should load the time tables page. | When the user clicks the 'Examinations' submenu 'Exam Time Tables', it loads the time tables page. | Pass
MG_EX_10 | Check whether clicking on the 'Examinations' submenu 'University Schools and Centres' loads a new page of the same. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'University Schools and Centres' submenu. |  | When the user clicks the 'Examinations' submenu 'University Schools and Centres', it should load a new page of the same. | When the user clicks the 'Examinations' submenu 'University Schools and Centres', it loads a new page of the same. | Pass
MG_EX_11 | Check whether clicking on the 'Examinations' submenu 'Fees' loads a new page for navigation to MGU e-Pay. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Fees' submenu. |  | When the user clicks the 'Examinations' submenu 'Fees', it should load a new page for navigation to MGU e-Pay. | When the user clicks the 'Examinations' submenu 'Fees', it loads a new page for navigation to MGU e-Pay. | Pass
MG_EX_12 | Check whether clicking on the 'Examinations' submenu 'Fees' loads the 'Fees related to Private Registration' pdf when 'Revised Fees' is clicked. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Fees' submenu. |  | When the user clicks the 'Examinations' submenu 'Fees', it should load 'Fees related to Private Registration' pdf when 'Revised Fees' is clicked. | When the user clicks the 'Examinations' submenu 'Fees', it loads 'Fees related to Private Registration' pdf when 'Revised Fees' is clicked. | Pass
MG_EX_13 | Check whether clicking on the 'Examinations' submenu 'Model Question Papers' loads a page with respective question papers in pdf format when clicked. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Model Question Papers' submenu. |  | When the user clicks the 'Examinations' submenu 'Model Question Papers', it should load a page with respective question papers in pdf format when clicked. | When the user clicks the 'Examinations' submenu 'Model Question Papers', it loads a page with respective question papers in pdf format when clicked. | Pass
MG_EX_14 | Check whether clicking on the submenu 'Model Question Papers', the links under the 'Model Question Paper of V and VI Semester UG Programmes under CBCSS 2013' is navigating correctly. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Model Question Papers' submenu. |  | When the user clicks the submenu 'Model Question Papers', the links under 'Model Question Paper of V and VI Semester UG Programmes under CBCSS 2013' should navigate correctly. | When the user clicks the submenu 'Model Question Papers', the links under 'Model Question Paper of V and VI Semester UG Programmes under CBCSS 2013' is not navigating correctly and moving to Homepage. | Fail
MG_EX_15 | Check whether clicking on the 'Examinations' submenu 'Rank/Position Notification' loads the notification of Ranks/Position. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Rank/Position Notification' submenu. |  | When the user clicks the 'Examinations' submenu 'Rank/Position Notification', it should load the notification of Ranks/Position. | When the user clicks the 'Examinations' submenu 'Rank/Position Notification', it loads the notification of Ranks/Position. | Pass
MG_EX_16 | Verify that the previous and next buttons at the bottom of the 'Rank/Position Notification' submenu page is working correctly. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Rank/Position Notification' submenu. 4.Locate the previous and next buttons at the bottom of the page. |  | When the user clicks the 'Examinations' submenu 'Rank/Position Notification', it should load a new page and the previous and next buttons at the bottom of the page must work correctly. | When the user clicks the 'Examinations' submenu 'Rank/Position Notification', it should load a new page and the previous and next buttons at the bottom of the page works correctly. | Pass

## Research
MG UNIVERSITY
Version of application : |  | Module name : Research |  |  | Tested by : Sadhika S
Verified by : Pradeep K C |  | Environment Details : Windows 11 |  |  | Date : 02-11-2023
Test id | Test Description | Test Procedure | Test Data | Exp Result | Actual Result | Status
MG_RS_01 | Verify that when a user clicks 'Research' option, Research Portal is opened. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. |  | When the user clicks the 'Research' section, it should load Research Portal. | When the user clicks the 'Examinations' section, it loads Research Portal. | Pass
MG_RS_02 | Verify that the section 'Research' contains a dropdown menu list. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. |  | The section 'Research' should have a dropdown menu list. | The section 'Research' has a dropdown menu list. | Pass
MG_RS_03 | Verify that when a user clicks 'Research' tab, the field gets highlighted. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. |  | When the user clicks the 'Research' tab, it should get highlighted. | When the user clicks the 'Research' tab, it does not gets highlighted. | Fail
MG_RS_04 | Check whether clicking on the 'Research' submenu 'Areas' loads the list of Faculty/Subject of the research areas. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Areas' submenu. |  | When the user clicks the 'Research' submenu 'Areas', it should load a page of Faculty/Subject of the research areas. | When the user clicks the 'Research' submenu 'Areas', it loads a page of Faculty/Subject of the research areas. | Pass
MG_RS_05 | Check whether clicking on the 'Research' submenu 'Research Centres' displays a list of the research colleges in alphabetical order. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Research Centres' submenu. |  | When the user clicks the 'Research' submenu 'Research Centres', it should list the research colleges in alphabetical order. | When the user clicks the 'Research' submenu 'Research Centres', it lists the research colleges in alphabetical order. | Pass
MG_RS_06 | Verify that the previous and next buttons at the bottom of the 'Research Centres' submenu page is working correctly. | 1.Open website www.mgu.ac.in 2.Locate the 'Examinations' section. 3.Click on 'Research Centres' submenu. 4.Locate the previous and next buttons at the bottom of the page. |  | When the user clicks the 'Research' submenu 'Research Centres', it should load a new page and the previous and next buttons at the bottom of the page must work correctly. | When the user clicks the 'Research' submenu 'Research Centres', it loads a new page and the previous and next buttons at the bottom of the page works correctly. | Pass
MG_RS_07 | Check whether clicking on the 'Research' submenu 'Research Centres', the Search tab is editable and the search symbol is clickable. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Research Centres' submenu. |  | When the user clicks the 'Research' submenu 'Research Centres', the Search tab should be editable and the search symbol must be clickable. | When the user clicks the 'Research' submenu 'Research Centres', the Search tab is editable and the search symbol is clickable. | Pass
MG_RS_08 | Check whether clicking on the 'Research' submenu 'Publications', loads the list of year-wise publications. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Publications' submenu. |  | When the user clicks the 'Research' submenu 'Publications', it should list the year-wise publications. | When the user clicks the 'Research' submenu 'Publications', it lists the year-wise publications. | Pass
MG_RS_09 | Check whether clicking on the 'Research' submenu 'Research Guides', loads the list of research guides present with their respective colleges. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Research Guides' submenu. |  | When the user clicks the 'Research' submenu 'Research Guides', it should list the research guides present with their respective colleges. | When the user clicks the 'Research' submenu 'Research Guides', it lists the research guides present with their respective colleges. | Pass
MG_RS_10 | Check whether clicking on the submenu 'Research Guides' gives the college details of a particular guide. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Research Guides' submenu. |  | When the user clicks the submenu 'Research Guides', it should display the college details of a particular guide. | When the user clicks the 'Research' submenu 'Research Guides',it displays the college details of a particular guide. | Pass
MG_RS_11 | Check whether clicking on the submenu 'Research Guides', the guide details can be searched based on name as well as subject. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Research Guides' submenu. |  | When the user clicks the submenu 'Research Guides', the details should be searched based on name as well as subject. | When the user clicks the submenu 'Research Guides', the details can be searched based on name as well as subject. | Pass
MG_RS_12 | Check whether clicking on the 'Research' submenu 'Funded Projects', loads the details of the projects been funded. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Funded Projects' submenu. |  | When the user clicks the 'Research' submenu 'Funded Projects', it must display the details of the projects been funded. | When the user clicks the 'Research' submenu 'Funded Projects', the page does not navigate. | Fail
MG_RS_13 | Check whether clicking on the 'Research' submenu 'Patents', the page loads the patents received for research projects. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Patents' submenu. |  | When the user clicks the 'Research' submenu 'Patents', it must display the patets received for research projects. | When the user clicks the 'Research' submenu 'Patents', it displays the patets received for research projects. | Pass
MG_RS_14 | Check whether clicking on the 'Research' submenu 'Conferences', loads a new page of conferences. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Conferences' submenu. |  | When the user clicks the 'Research' submenu 'Conferences', it must load a new page of conferences. | When the user clicks the 'Research' submenu 'Conferences', the page does not navigate. | Fail
MG_RS_15 | Check whether clicking on the 'Research' submenu 'Ph.D. Awardees', loads a new page of year-wise Ph.D holders list. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Ph.D. Awardees' submenu. |  | When the user clicks the 'Research' submenu 'Ph.D. Awardees', it must load a new page of year-wise Ph.D. holders list. | When the user clicks the 'Research' submenu 'Ph.D. Awardees', it loads a new page of year-wise Ph.D. holders list. | Pass
MG_RS_16 | Check whether clicking on the 'Research' submenu 'Research Committees', loads a new page of members of the University Research Committee. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Research Committees' submenu. |  | When the user clicks the 'Research' submenu 'Research Committees', it must load a new page of the University Research Committee. | When the user clicks the 'Research' submenu 'Research Committees', it loads a new page of the University Research Committee. | Pass
MG_RS_17 | Check whether clicking on the 'Research' submenu 'Resources',loads a short note on the resources. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Resources' submenu. |  | When the user clicks the 'Research' submenu 'Resources', it must load a short note on the resources. | When the user clicks the 'Research' submenu 'Resources', it loads a short note on the resources. | Pass
MG_RS_18 | Check whether clicking on the 'Research' submenu 'Projects',loads a new page of projects. | 1.Open website www.mgu.ac.in 2.Locate the 'Research' section. 3.Click on 'Projects' submenu. |  | When the user clicks the 'Research' submenu 'Projects', it must load a new page of projects. | When the user clicks the 'Research' submenu 'Projects', it does not load projects page and a blank page is displayed. | Fail

## Central Facilities
MG UNIVERSITY
Version of application : |  | Module name : Central Facilities |  |  | Tested by : Sadhika S
Verified by : Pradeep K C |  | Environment Details : Windows 11 |  |  | Date : 06-11-2023
Test id | Test Description | Test Procedure | Test Data | Exp Result | Actual Result | Status
MG_CF_01 | Verify that when a user clicks 'Central Facilities' option,the facilities at the university page is opened. | 1.Open website www.mgu.ac.in 2.Locate the 'Central Facilities' section. |  | When the user clicks the 'Central Facilities' section, it should load the facilities at the university page. | When the user clicks the 'Central Facilities' section, it loads the facilities at the university page. | Pass
MG_CF_02 | Verify that the section 'Central Facilities' contains a dropdown menu list. | 1.Open website www.mgu.ac.in 2.Locate the 'Central Facilities' section. |  | The section 'Central Facilities' should have a dropdown menu list. | The section 'Central Facilities' has a dropdown menu list. | Pass
MG_CF_03 | Verify that when a user clicks 'Central Facilities' tab, the field gets highlighted. | 1.Open website www.mgu.ac.in 2.Locate the 'Central Facilities' section. |  | When the user clicks the 'Central Facilities' tab, it should get highlighted. | When the user clicks the 'Central Facilities' tab, it does not gets highlighted. | Fail
MG_CF_04 | Check whether clicking on the 'Central Facilities' submenu 'Physical Infrastructure' loads the infrastructure details. | 1.Open website www.mgu.ac.in 2.Locate the 'Central Facilities' section. 3.Click on 'Physical Infrastructure' submenu. |  | When the user clicks the 'Central Facilities' submenu 'Physical Infrastructure', it should load a page of Faculty/Subject of the research areas. | When the user clicks the 'Central Facilities' submenu 'Physical Infrastructure', it loads a page of Faculty/Subject of the research areas. | Pass
MG_CF_05 | Check whether clicking on the 'Central Facilities' submenu 'Lab Infrastructure' loads the infrastructure details. | 1.Open website www.mgu.ac.in 2.Locate the 'Central Facilities' section. 3.Click on 'Lab Infrastructure' submenu. |  | When the user clicks the 'Central Facilities' submenu 'Lab Infrastructure', it should load a page of Lab facilities. | When the user clicks the 'Central Facilities' submenu 'Lab Infrastructure', it loads a page of Lab facilities. | Pass
MG_CF_06 | Check whether clicking on the 'Central Facilities' submenu 'Library' loads the details and contact of the university library. | 1.Open website www.mgu.ac.in 2.Locate the 'Central Facilities' section. 3.Click on 'Library' submenu. |  | When the user clicks the 'Central Facilities' submenu 'Library', it should load the details and contact of the university library. | When the user clicks the 'Central Facilities' submenu 'Library', it loads the details and contact of the university library. | Pass
MG_CF_07 | Verify that on the submenu 'Library' page, the given link of the library is clickable and navigates to library details page. | 1.Open website www.mgu.ac.in 2.Locate the 'Central Facilities' section. 3.Click on 'Library' submenu. 4.Open www.library.mgu.ac.in |  | When the user clicks the submenu 'Library', it should load the link of library and must be clickable. | When the user clicks the submenu 'Library', it loads the link of library and must be clickable. | Pass
MG_CF_08 | Check whether clicking on the 'Central Facilities' submenu 'Water Harvesting' loads the page of Raveendra Sarovaram. | 1.Open website www.mgu.ac.in 2.Locate the 'Central Facilities' section. 3.Click on 'Water Harvesting' submenu. |  | When the user clicks the 'Central Facilities' submenu 'Water Harvesting', it should load the page of Raveendra Sarovaram. | When the user clicks the 'Central Facilities' submenu 'Water Harvesting', it loads the page of Raveendra Sarovaram. | Pass
MG_CF_09 | Check whether clicking on the 'Central Facilities' submenu 'Miyawaki' loads the page of afforestation programme details. | 1.Open website www.mgu.ac.in 2.Locate the 'Central Facilities' section. 3.Click on 'Miyyawaki' submenu. |  | When the user clicks the 'Central Facilities' submenu 'Miyawaki', it should load the page of afforestation programme. | When the user clicks the 'Central Facilities' submenu 'Miyawaki', it loads the page of afforestation programme. | Pass

## Learning Resources
MG UNIVERSITY
Version of application : |  | Module name : Learning Resources |  |  | Tested by : Sadhika S
Verified by : Pradeep K C |  | Environment Details : Windows 11 |  |  | Date : 10-112023
Test id | Test Description | Test Procedure | Test Data | Exp Result | Actual Result | Status
MG_LR_01 | Verify that when a user clicks 'Learning Resources' option,the e-learning Resources page is opened. | 1.Open website www.mgu.ac.in 2.Locate the 'Learning Resources' section. |  | When the user clicks the 'Learning Resources' section, it should load e-learning Resources page. | When the user clicks the 'Learning Resources' section, it loads the e-learning Resources page. | Pass
MG_LR_02 | Verify that the section 'Learning Resources' contains a dropdown menu list. | 1.Open website www.mgu.ac.in 2.Locate the 'Learning Resources' section. |  | The section 'Learning Resources' should have a dropdown menu list. | The section 'Learning Resources' has a dropdown menu list. | Pass
MG_LR_03 | Verify that when a user clicks 'Learning Resources' tab, the field gets highlighted. | 1.Open website www.mgu.ac.in 2.Locate the 'Learning Resources' section. |  | When the user clicks the 'Learning Resources' tab, it should get highlighted. | When the user clicks the 'Learning Resources' tab, it does not gets highlighted. | Fail
MG_LR_04 | Check whether clicking on the 'Learning Resources' submenu 'SWAYAM' loads the MGU SWAYAM page. | 1.Open website www.mgu.ac.in 2.Locate the 'Learning Resources' section. 3.Click on 'SWAYAM' submenu. |  | When the user clicks the 'Learning Resources' submenu 'SWAYAM', it should load MGU SWAYAM page. | When the user clicks the 'Learning Resources' submenu 'SWAYAM', it loads MGU SWAYAM page. | Pass
MG_LR_05 | Check whether clicking on the 'Learning Resources' submenu 'MOOC' loads the MOOC(Massive Open Online Courses) page. | 1.Open website www.mgu.ac.in 2.Locate the 'Learning Resources' section. 3.Click on 'MOOC' submenu. |  | When the user clicks the 'Learning Resources' submenu 'MOOC', it should load MOOC(Massive Open Online Courses) page. | When the user clicks the 'Learning Resources' submenu 'mooc', it loads MOOC(Massive Open Online Courses) page. | Pass
MG_LR_06 | Check whether clicking on the 'Learning Resources' submenu 'Spoken Tutorial(ST)' loads the Spoken Tutorial(ST) Programme page. | 1.Open website www.mgu.ac.in 2.Locate the 'Learning Resources' section. 3.Click on 'Spoken Tutorial(ST)' submenu. |  | When the user clicks the 'Learning Resources' submenu 'Spoken Tutorial(ST)', it should load Spoken Tutorial(ST) Programme page. | When the user clicks the 'Learning Resources' submenu 'Spoken Tutorial(ST)', it loads Spoken Tutorial(ST) Programme page. | Pass
MG_LR_07 | Check whether clicking on the 'Learning Resources' submenu 'GIAN' loads the Global Initiative of Academic Networks (GIAN) page. | 1.Open website www.mgu.ac.in 2.Locate the 'Learning Resources' section. 3.Click on 'GIAN' submenu. |  | When the user clicks the 'Learning Resources' submenu 'GIAN', it should load Global Initiative of Academic Networks (GIAN) page. | When the user clicks the 'Learning Resources' submenu 'GIAN', it loads Global Initiative of Academic Networks (GIAN) page. | Pass
MG_LR_08 | Check whether clicking on the 'Learning Resources' submenu 'Virtual Lab' loads the description of virtual labs in a new page. | 1.Open website www.mgu.ac.in 2.Locate the 'Learning Resources' section. 3.Click on 'Virtual Lab' submenu. |  | When the user clicks the 'Learning Resources' submenu 'Virtual Lab', it should load a description of virtual labs in a new page. | When the user clicks the 'Learning Resources' submenu 'Virtual Lab', it loads a description of virtual labs in a new page. | Pass
MG_LR_09 | Check whether clicking on the link in submenu 'Virtual Lab' opens the Virtual Labs portal. | 1.Open website www.mgu.ac.in 2.Locate the 'Learning Resources' section. 3.Click on 'Virtual Lab' submenu. 4.Locate the link 'Virtual Labs'. |  | When the user clicks the link in submenu 'Virtual Lab', it should open the Virtual Labs portal. | When the user clicks the link in submenu 'Virtual Lab', it opens the Virtual Labs portal. | Pass
MG_LR_10 | Check whether clicking on the 'Learning Resources' submenu 'STRIDE' loads the Scheme for Trans-Disciplinary Research for India's Developing Economy page. | 1.Open website www.mgu.ac.in 2.Locate the 'Learning Resources' section. 3.Click on 'STRIDE' submenu. |  | When the user clicks the 'Learning Resources' submenu 'STRIDE', it should load the Scheme for Trans-Disciplinary Research for India's Developing Economy page. | When the user clicks the 'Learning Resources' submenu 'STRIDE', it loads the Scheme for Trans-Disciplinary Research for India's Developing Economy page. | Pass
MG_LR_11 | Check whether clicking on the 'Learning Resources' submenu 'IMPRESS' loads the Impactful Policy Research in Social Science pdf page. | 1.Open website www.mgu.ac.in 2.Locate the 'Learning Resources' section. 3.Click on 'IMPRESS' submenu. |  | When the user clicks the 'Learning Resources' submenu 'IMPRESS', it should load the Impactful Policy Research in Social Science pdf page. | When the user clicks the 'Learning Resources' submenu 'IMPRESS', it loads the Impactful Policy Research in Social Science pdf page. | Pass
MG_LR_12 | Check whether clicking on the 'Learning Resources' submenu 'Vidyamrutham' loads the Open Online Courses page. | 1.Open website www.mgu.ac.in 2.Locate the 'Learning Resources' section. 3.Click on 'Vidyamrutham' submenu. |  | When the user clicks the 'Learning Resources' submenu 'Vidyamrutham', it should load the Open Online Courses page. | When the user clicks the 'Learning Resources' submenu 'Vidyamrutham', it loads the Open Online Courses page. | Pass

## Infodesk
MG UNIVERSITY
Version of application : |  | Module name : Infodesk |  |  | Tested by : Sadhika S
Verified by : Pradeep K C |  | Environment Details : Windows 11 |  |  | Date : 11-11-2023
Test id | Test Description | Test Procedure | Test Data | Exp Result | Actual Result | Status
MG_ID_01 | Verify that when a user clicks 'Infodesk' option, the information about different departments is displayed in short. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. |  | When the user clicks the 'Learning Resources' section, it should display information about different departments in short. | When the user clicks the 'Infodesk' section, it displays information about different departments in short. | Pass
MG_ID_02 | Verify that the section 'Infodesk' contains a dropdown menu list. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. |  | The section 'Infodesk' should have a dropdown menu list. | The section 'Infodesk' has a dropdown menu list. | Pass
MG_ID_03 | Verify that when a user clicks 'Infodesk' tab, the field gets highlighted. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. |  | When the user clicks the 'Infodesk' tab, it should get highlighted. | When the user clicks the 'Infodesk' tab, it does not gets highlighted. | Fail
MG_ID_04 | Check whether clicking on the 'Infodesk' submenu 'FAQ' loads the questions page. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'FAQ' submenu. |  | When the user clicks the 'Infodesk' submenu 'FAQ', it should load the questions page. | When the user clicks the 'Infodesk' submenu 'FAQ', it loads the questions page. | Pass
MG_ID_05 | Check whether clicking on the 'Infodesk' submenu 'Announcements' loads the announcements according to the dates order. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Announcements' submenu. |  | When the user clicks the 'Infodesk' submenu 'Announcements', it should load the announcements according to the dates order. | When the user clicks the 'Infodesk' submenu 'Announcements', it loads the announcements according to the dates order. | Pass
MG_ID_06 | Check whether clicking on the 'Infodesk' submenu 'Academic Events' loads the events according to the dates order. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Academic Events' submenu. |  | When the user clicks the 'Infodesk' submenu 'Academic Events', it should load the events according to the dates order. | When the user clicks the 'Infodesk' submenu 'Academic Events', it should load the events according to the dates order. | Pass
MG_ID_07 | Check whether clicking on the 'Infodesk' submenu 'Orders' loads the university orders according to the dates order. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Orders' submenu. |  | When the user clicks the 'Infodesk' submenu 'Orders', it should load the university orders according to the dates order. | When the user clicks the 'Infodesk' submenu 'Orders', it loads the university orders according to the dates order. | Pass
MG_ID_08 | Check whether clicking on the 'Infodesk' submenu 'Circulars' loads the university circulars according to the dates order. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Circulars' submenu. |  | When the user clicks the 'Infodesk' submenu 'Circulars', it should load the university circulars according to the dates order. | When the user clicks the 'Infodesk' submenu 'Circulars', it loads the university circulars according to the dates order. | Pass
MG_ID_09 | Check whether clicking on the 'Infodesk' submenu 'Notifications' loads the university notifications according to the dates order. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Notifications' submenu. |  | When the user clicks the 'Infodesk' submenu 'Notifications', it should load the university notifications according to the dates order. | When the user clicks the 'Infodesk' submenu 'Notifications', it loads the university notifications according to the dates order. | Pass
MG_ID_10 | Check whether clicking on the 'Infodesk' submenu 'Press Release' loads the press release details according to the dates order. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Press Release' submenu. |  | When the user clicks the 'Infodesk' submenu 'Press Release', it should load the press release details according to the dates order. | When the user clicks the 'Infodesk' submenu 'Press Release', it loads the press release details according to the dates order. | Pass
MG_ID_11 | Check whether clicking on the 'Infodesk' submenu 'Tenders & Quotations' loads the tenders & quotations page according to the dates order. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Tenders & Quotations' submenu. |  | When the user clicks the 'Infodesk' submenu 'Tenders & Quotations', it should load the tenders & quotations page according to the dates order. | When the user clicks the 'Infodesk' submenu 'Tenders & Quotations', it loads the tenders & quotations page according to the dates order. | Pass
MG_ID_12 | Check whether clicking on the 'Infodesk' submenu 'Vacancies' loads the vacancies in university according to the dates order. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Vacancies' submenu. |  | When the user clicks the 'Infodesk' submenu 'Vacancies', it should load the vacancies in university according to the dates order. | When the user clicks the 'Infodesk' submenu 'Vacancies', it loads the vacancies in university according to the dates order. | Pass
MG_ID_13 | Check whether clicking on the 'Infodesk' submenu 'Ranklists' loads the Ranklist Archives according to the dates order. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Ranklists' submenu. |  | When the user clicks the 'Infodesk' submenu 'Ranklists', it should load the Ranklist Archives according to the dates order. | When the user clicks the 'Infodesk' submenu 'Ranklists', it loads the Ranklist Archives according to the dates order. | Pass
MG_ID_14 | Check whether clicking on the 'Infodesk' submenu 'Endorsement' loads the Endorsement Archives according to the dates order. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Endorsement' submenu. |  | When the user clicks the 'Infodesk' submenu 'Endorsement', it should load the Endorsement Archives according to the dates order. | When the user clicks the 'Infodesk' submenu 'Endorsement', it loads the Endorsement Archives according to the dates order. | Pass
MG_ID_15 | Check whether clicking on the 'Infodesk' submenu 'Calendar' loads the academic and examination calendars links. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Calendar' submenu. |  | When the user clicks the 'Infodesk' submenu 'Calendar', it should load the academic and examination calendars links. | When the user clicks the 'Infodesk' submenu 'Calendar', it loads the academic and examination calendars links. | Pass
MG_ID_16 | Verify that the in submenu 'Calendar', the academic and examination calendars links are clickable. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Calendar' submenu. |  | When the user clicks the links in the submenu 'Calendar', it must be clickable. | When the user clicks the links in the submenu 'Calendar', it is clickable. | Pass
MG_ID_17 | Check whether clicking on the 'Infodesk' submenu 'Various Items' loads a new page of other programmes of the university. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Various Items' submenu. |  | When the user clicks the 'Infodesk' submenu 'Various Items', it should load a new page of other programmes of the university. | When the user clicks the 'Infodesk' submenu 'Various Items', it loads a new page of other programmes of the university. | Pass
MG_ID_18 | Check whether clicking on the 'Infodesk' submenu 'Scholarships & Financial Assistance' loads a page with scholarship & fellowship details. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Scholarships & Financial Assistance' submenu. |  | When the user clicks the 'Infodesk' submenu 'Scholarships & Financial Assistance', it should load a page with scholarship & fellowship details. | When the user clicks the 'Infodesk' submenu 'Scholarships & Financial Assistance', it loads a page with scholarship & fellowship details. | Pass
MG_ID_19 | Verify that the in submenu 'Scholarships & Financial Assistance', each scholarship link is clickable. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Scholarships & Financial Assistance' submenu. |  | When the user clicks the links in the submenu 'Scholarships & Financial Assistance', it must be clickable. | When the user clicks the links in the submenu 'Scholarships & Financial Assistance', it is clickable. | Pass
MG_ID_20 | Check whether clicking on the 'Infodesk' submenu 'Downloads' opens a page with downloadable forms. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Downloads' submenu. |  | When the user clicks the 'Infodesk' submenu 'Downloads', it should open a page with downloadable forms. | When the user clicks the 'Infodesk' submenu 'Downloads', it opens a page with downloadable forms. | Pass
MG_ID_21 | Check whether clicking on the 'Infodesk' submenu 'Fees' opens a pdf file of the fees structure of each section. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Fees' submenu. |  | When the user clicks the 'Infodesk' submenu 'Fees', it should open a pdf file of the fees structure of each section. | When the user clicks the 'Infodesk' submenu 'Fees', it opens a pdf file of the fees structure of each section. | Pass
MG_ID_22 | Check whether clicking on the 'Infodesk' submenu 'Contact Us' opens a page of contact details of the university. | 1.Open website www.mgu.ac.in 2.Locate the 'Infodesk' section. 3.Click on 'Contact Us' submenu. |  | When the user clicks the 'Infodesk' submenu 'Contact Us', it should open a page of contact details of the university. | When the user clicks the 'Infodesk' submenu 'Contact Us', it opens a page of contact details of the university. | Pass

## Student Portals
MG UNIVERSITY
Version of application : |  | Module name : Student Portals |  |  | Tested by : Sadhika S
Verified by : Pradeep K C |  | Environment Details : Windows 11 |  |  | Date : 18-11-2023
Test id | Test Description | Test Procedure | Test Data | Exp Result | Actual Result | Status
MG_SP_01 | Verify that when a user clicks 'Student Portals' option, the students page is opened. | 1.Open website www.mgu.ac.in 2.Locate the 'Student Portals' section. |  | When the user clicks the 'Student Portals' section, it should open the students page. | When the user clicks the 'Student Portals' section, it does not opens the students page and is redirecting to homepage. | Fail
MG_SP_02 | Verify that the section 'Student Portals' contains a dropdown menu list. | 1.Open website www.mgu.ac.in 2.Locate the 'Student Portals' section. |  | The section 'Student Portals' should have a dropdown menu list. | The section 'Student Portals' has a dropdown menu list. | Pass
MG_SP_03 | Verify that when a user clicks 'Student Portals' tab, the field gets highlighted. | 1.Open website www.mgu.ac.in 2.Locate the 'Student Portals' section. |  | When the user clicks the 'Student Portals' tab, it should get highlighted. | When the user clicks the 'Student Portals' tab, it does not gets highlighted. | Fail
MG_SP_04 | Check whether clicking on the 'Student Portals' submenu 'E Payment Portal' loads the MGU e-Pay portal. | 1.Open website www.mgu.ac.in 2.Locate the 'Student Portals' section. 3.Click on 'E Payment Portal' submenu. |  | When the user clicks the 'Student Portals' submenu 'E Payment Portal', it should load the MGU e-Pay portal. | When the user clicks the 'Student Portals' submenu 'E Payment Portal', it loads the MGU e-Pay portal. | Pass
MG_SP_05 | Check whether clicking on the 'Student Portals' submenu 'Exam Registration' loads the supplementary exam registration page. | 1.Open website www.mgu.ac.in 2.Locate the 'Student Portals' section. 3.Click on 'Exam Registration' submenu. |  | When the user clicks the 'Student Portals' submenu 'Exam Registration', it should load the supplementary exam registration page. | When the user clicks the 'Student Portals' submenu 'Exam Registration', it loads the supplementary exam registration page. | Pass
MG_SP_06 | Check whether clicking on the 'Student Portals' submenu 'Revaluation Portal' loads the student portal login for revaluation. | 1.Open website www.mgu.ac.in 2.Locate the 'Student Portals' section. 3.Click on 'Revaluation Portal' submenu. |  | When the user clicks the 'Student Portals' submenu 'Revaluation Portal', it should load the student portal login for revaluation. | When the user clicks the 'Student Portals' submenu 'Revaluation Portal', it loads the student portal login for revaluation. | Pass
MG_SP_07 | Check whether clicking on the 'Student Portals' submenu 'Online Certificate Portal' loads the student portal for online applications. | 1.Open website www.mgu.ac.in 2.Locate the 'Student Portals' section. 3.Click on 'Online Certificate Portal' submenu. |  | When the user clicks the 'Student Portals' submenu 'Online Certificate Portal', it should load the student portal for online applications. | When the user clicks the 'Student Portals' submenu 'Online Certificate Portal', it loads the student portal for online applications. | Pass
MG_SP_08 | Check whether clicking on the 'Student Portals' submenu 'Online Application Portal' loads a new page for application. | 1.Open website www.mgu.ac.in 2.Locate the 'Student Portals' section. 3.Click on 'Online Application Portal' submenu. |  | When the user clicks the 'Student Portals' submenu 'Online Application Portal', it should load a new page for application. | When the user clicks the 'Student Portals' submenu 'Online Application Portal', it loads a new page for application. | Pass
MG_SP_09 | Check whether clicking on the 'Student Portals' submenu 'Students Grievances Portal' loads MGU Grievance Redressal System page. | 1.Open website www.mgu.ac.in 2.Locate the 'Student Portals' section. 3.Click on 'Students Grievances Portal' submenu. |  | When the user clicks the 'Student Portals' submenu 'Students Grievances Portal', it should load MGU Grievance Redressal System page. | When the user clicks the 'Student Portals' submenu 'Students Grievances Portal', it loadS MGU Grievance Redressal System page. | Pass

## Bug Report
BUG REPORT - MG UNIVERSITY
Version of application : |  | Module name : |  | Identified by : Sadhika S
Reported to : Pradeep K C |  | Environment details : Windows 11 |  | Date : 18-11-2023
Bug id | Test id | Bug Description | Severity | Priority | Screenshot | Status
Def_MG_01 | MG_HM_10 | The previous button does not display previous image in the slideshow. | Major | Low | https://drive.google.com/file/d/1vhhxTTImBV6M10n5fbhQPsLWeCwmqmg5/view?usp=drive_link | New
Def_MG_02 | MG_HM_36 | The webpage does not load the twitter login page at the bottom left corner. | Minor | Medium | https://drive.google.com/file/d/1vVKsVx2ugliCwkTq9SPfBe0O68G9g-Ad/view?usp=drive_link | New
Def_MG_03 | MG_AB_02 | When the user clicks the 'About' tab, it does not gets highlighted. | Major | High | https://drive.google.com/file/d/16isM6U0a5sOedWvfWg7ACQcw2Cvut2yh/view?usp=drive_link | New
Def_MG_04 | MG_AD_03 | When the user clicks the 'Administration' tab, it does not gets highlighted. | Major | High | https://drive.google.com/file/d/1ci6PYBuNw-MrcKtGJos8oi4jZ_ZSul8A/view?usp=drive_link | New
Def_MG_05 | MG_AD_07 | When the user clicks on the 'Administration' submenu 'Pro-Vice Chancellor', it does not load the details of the Pro-Vice Chancellor and 'page not found' meassage comes. | Major | Medium | https://drive.google.com/file/d/1zHTariD2OB8jynl1dmjqaFcNpnbNZ2Mr/view?usp=drive_link | New
Def_MG_06 | MG_AD_19 | 'Board of Studies in Departments of the University' submenu under Statutory Bodies is not clickable. | Major | High | https://drive.google.com/file/d/1vKaKNrME9C9iO_KkVTOdKj-ZwL1HunQt/view?usp=drive_link | New
Def_MG_07 | MG_AD_20 | 'Students Council' submenu under Statutory Bodies is not clickable. | Minor | Medium | https://drive.google.com/file/d/1NI7RmLYhIwf4hbugiqklL81kds4rc9p-/view?usp=drive_link | New
Def_MG_08 | MG_AC_03 | When the user clicks the 'Academics' tab, it does not gets highlighted. | Major | High | https://drive.google.com/file/d/1-zsIamWRP7ionLZyO3_bPiuhj4gPa6vO/view?usp=drive_link | New
Def_MG_09 | MG_AC_06 | When the user clicks the 'Academics' submenu 'International Centres', the two centres listed are not clickable. | Major | High | https://drive.google.com/file/d/1J1YC3Qg5HmIM9SeCLtqhz4vlktY6Tdf3/view?usp=drive_link | New
Def_MG_10 | MG_AC_17 | When the user clicks 'Syllabus for all programmes' under 'Programmes' submenu, the page does not load the syllabus details and 'page not found' message comes. | Critical | High | https://drive.google.com/file/d/1Ui_LzoffT0dqwc6vAj5k53B-eVRG43SP/view?usp=drive_link | New
Def_MG_11 | MG_AM_03 | When the user clicks the 'Admissions' tab, it does not gets highlighted. | Major | High | https://drive.google.com/file/d/1dXTA4roNkUgGV3UEvjqA2X9HWLkzGr8w/view?usp=drive_link | New
Def_MG_12 | MG_AM_04 | When the user clicks the 'Admissions' submenu 'Study @MGU- Schools/Centres (CAT)', it shows an error page. | Critical | High | https://drive.google.com/file/d/1fCFv3vQW3u4grVy838kTqJJmnXu6CaBb/view?usp=drive_link | New
Def_MG_13 | MG_AM_08 | When the user clicks the 'Admissions' submenu 'Integrated Programmes', it does not load a new page and shows an error message. | Critical | High | https://drive.google.com/file/d/1Nr-7wHdoJ-64qYK7W9-KIGVAO9m9DiFl/view?usp=drive_link | New
Def_MG_14 | MG_AM_09 | When the user clicks the 'Admissions' submenu 'M Phil', it shows a 'page not found' error message. | Critical | High | https://drive.google.com/file/d/1Y0tndknVc3p5eWsLFO6ojHurR87Lq9v6/view?usp=drive_link | New
Def_MG_15 | MG_AM_10 | When the user clicks the 'Admissions' submenu 'MBA (SMBS)', it shows an error message. | Critical | High | https://drive.google.com/file/d/1MdJ5donLvTIhvISfWrPZGF3i7LJmYUEi/view?usp=drive_link | New
Def_MG_16 | MG_EX_03 | When the user clicks the 'Examinations' tab, it does not gets highlighted. | Major | High | https://drive.google.com/file/d/1-UCgRZhoSgu5-fFf6L6frkLFwOxb-Y2j/view?usp=drive_link | New
Def_MG_17 | MG_EX_14 | When the user clicks the submenu 'Model Question Papers', the links under 'Model Question Paper of V and VI Semester UG Programmes under CBCSS 2013' is not navigating correctly and moving to Homepage. | Critical | High | https://drive.google.com/file/d/1n8EGNQqWDezfOS5mWKYWrZ5wzmP1w9Gw/view?usp=drive_link | New
Def_MG_18 | MG_RS_03 | When the user clicks the 'Research' tab, it does not gets highlighted. | Major | High | https://drive.google.com/file/d/1r8ig489mGYhvFB2IP9AZTB7iDVi_5mqy/view?usp=drive_link | New
Def_MG_19 | MG_RS_12 | When the user clicks the 'Research' submenu 'Funded Projects', the page does not navigate. | Critical | High | https://drive.google.com/file/d/10o45iEWGAXWfRO7aW6eglRMIS6PM0koS/view?usp=drive_link | New
Def_MG_20 | MG_RS_14 | When the user clicks the 'Research' submenu 'Conferences', the page does not navigate. | Critical | High | https://drive.google.com/file/d/1byxYhP4hv5NMjLngoCwdO6ylifdbIsyG/view?usp=drive_link | New
Def_MG_21 | MG_RS_18 | When the user clicks the 'Research' submenu 'Projects', it does not load projects page and a blank page is displayed. | Critical | High | https://drive.google.com/file/d/1iG6VqQTUWLImyQowEib9yACNdT9ooMWm/view?usp=drive_link | New
Def_MG_22 | MG_CF_03 | When the user clicks the 'Central Facilities' tab, it does not gets highlighted. | Major | High | https://drive.google.com/file/d/1buw-PzXHuA1mf4avK2YDtYmHtigE2UZn/view?usp=drive_link | New
Def_MG_23 | MG_LR_03 | When the user clicks the 'Learning Resources' tab, it does not gets highlighted. | Major | High | https://drive.google.com/file/d/1j_VJ-21l_7wp6rHoR-JgLJgvuC1uiz-O/view?usp=drive_link | New
Def_MG_24 | MG_ID_03 | When the user clicks the 'Infodesk' tab, it does not gets highlighted. | Major | High | https://drive.google.com/file/d/1bXhhPyGLS3Dr_EOFlXHzXChjWrXgio4I/view?usp=drive_link | New
Def_MG_25 | MG_SP_01 | When the user clicks the 'Student Portals' section, it does not opens the students page and is redirecting to homepage. | Critical | High | https://drive.google.com/file/d/10C7WLfMB7SBqmOweyLQG42vN0NqU5F6S/view?usp=drive_link | New
Def_MG_26 | MG_SP_03 | When the user clicks the 'Student Portals' tab, it does not gets highlighted. | Major | High | https://drive.google.com/file/d/19b-BJpRgPtQLNc8_T-SUD5Z1o3-7w1Lb/view?usp=drive_link | New

## Defect Distribution
Test Report : MG University, Kerala
| Home | 54
| About | 14
| Administration | 29
| Academics | 18
| Admissions | 16
| Examinations | 16
| Research | 18
| Central Facilities | 9
| Learning Resources | 12
| Infodesk | 22
| Student Portals | 9
| Total Test Cases | 217
| Failed | 26
| Passed | 191